## Sheet1
User Type	Functional Requirement (Epic)	User Story Number	User Story / Task	Acceptance Criteria	Priority	Release
Shipping Team	Data Gathering and Processing	USN-1	Gather shipping data from e-commerce orders	- Connect with the e-commerce platform to collect order and shipping data.<br> - Store this data in our central database.	High	Sprint-1
Data Analyst	Historical Data Analysis and Insights	USN-2	Analyze historical shipping data	- Clean and analyze past shipping data to uncover patterns.	High	Sprint-1
Data Scientist	Predictive Model Development	USN-3	Create a predictive model for shipping times	- Develop a machine learning model using historical data.<br> - Train it to make accurate shipping time predictions.	High	Sprint-2
Data Scientist	Model Testing and Refinement	USN-4	Evaluate the accuracy of the shipping time model	- Thoroughly test the model's accuracy and performance.<br> - Fine-tune the model for better predictions.	High	Sprint-2
IT Team	Integration with E-commerce Platform	USN-5	Integrate the prediction model with our e-commerce platform	- Link the model to the e-commerce platform for real-time predictions.<br> - Ensure seamless integration for our users.	High	Sprint-3
Customer Support	Real-time Shipment Tracking	USN-6	Provide real-time shipment tracking to our customers	- Implement a tracking feature on our e-commerce website.<br> - Ensure our customers can see real-time status updates.	High	Sprint-3
Data Analyst	Model Performance Monitoring	USN-7	Continuously monitor model performance and create reports	- Set up ongoing monitoring of model accuracy.<br> - Generate regular reports for all stakeholders.	High	Sprint-4
Data Scientist	Model Maintenance and Improvement	USN-8	Maintain and enhance the shipping prediction model	- Regularly update the model with new data.<br> - Enhance its accuracy over time for better predictions.	High	Sprint-4
Customer Support	User Feedback Collection and Analysis	USN-9	Gather and analyze user feedback on the shipping predictions	- Collect feedback from users regarding the accuracy of our predictions.<br> - Analyze the feedback to make necessary improvements.	High	Sprint-4
Data Engineer	Data Infrastructure Review and Scaling	USN-10	Ensure our data infrastructure supports model requirements	- Review data storage and processing capacity.<br> - Make necessary adjustments to ensure our model can scale effectively.	High	Sprint-1
IT Team	Data Security and Privacy	USN-11	Guarantee data security and privacy for our shipping data	- Implement security measures to protect sensitive shipping data.<br> - Comply with data protection regulations to safeguard user data.	High	Sprint-1
Marketing Team	User-friendly Communication	USN-12	Communicate shipping predictions to our users	- Create clear and user-friendly notifications regarding estimated delivery times.<br> - Ensure timely and transparent communication with our users.	High	Sprint-3